## Slide 1: How quarterly Work Plans are built Training on Planning, Budgeting, Controls, Cash flow and government financial rules for government Health Staff Nay Pyi Taw

## Slide 2: Outlines
Formulation of Annual Work plan
Development of quarterly work plan
Preparation and requirement
Highlights to be taken care of

## Slide 3: Formulation of Annual work plan
National Annual work plan is developed according to:
National Strategic Plan
Performance framework and PSM plan
TSG guidance
MHSCC endorsement
GF endorsement and approval

## Slide 4
Bottom up planning through S/R coordination meeting or work plan development meeting where State and Regional level activities, District/Township level activities and Community level activities are planned
What, How, Who, Where, When, Which payment modality to be used, for activities are discussed
Central level activities are compiled together during quarterly work plan development meeting at central
Detail of work plan for all level activities are finalized at this meeting
Development of quarterly work plan

## Slide 5: Development of quarterly work plan
Detail Assumptions (Bottom up planning)
Budget
Budgeted Work Plan (Activity summary sheet)
Activity implementation
Activity 1 (TRC e.g., Training, Meeting, PSM, M&E, LLIN distribution)- Per diem, TA or travel subsidy or fuel cost, Accommodation, Miscellaneous)
Activity 2 (Patient/Provider support: Travel, Incentive/Per diem)
Other Activities (Lab Support, Procurement-IEC/promotional, Maintenance, Renovation, RDS center hiring, outsourcing e.g., warehouse, insurance)
Activity Name
Payment Modality (Direct, Reimbursement, Advance)
Budget code
Period or Date
S/R/Township/Site (FFA budget allocation, Management by S/R for awareness of all activities)
Planned Budget (Per diem, Travel cost, - for disbursement; training)
Facilitators, Participants, Secretariats (For planning)
Report (Variance Explanation)
Application of lessons learned for future planning (NSP, Annual budgeted WP)

## Slide 6: Preparation and requirement
Before conducting each QWP meeting, the activities completion, the remaining activities to be conducted, available budget, expenditure, budget balance, pipe line expenditure, procurement related activities,
Activities from budget template are transformed into the work plan format, in excel, and are shared to the participants, prior to the work plan preparation meeting for their inputs, discussion and finalization
Compilation of all pieces of planned activities, followed by proper review in terms of frequency, budget and compliance to approved budget and SOP
Follow up/ways to expedite pending activities is also discussed during the work plan

## Slide 7
After compiling the work plan, UNOPS team (Programme, MCFU, PSM) supports assuring the work plan is as per the SOP and the GF approved budget
At UNOPS, the 3 diseases work plan are compiled and schedule conflict for major direct disbursed activities are negotiated for convenient/timely disbursement.
The compiled work plan is also used for the planning of disbursement by MCFU (amount of cash to be transferred to each FFA)
Distribution of work plan to the S/R followed by sharing with the township implementing sites
Preparation and requirement (Contd)

## Slide 8: Highlights to be taken care of
During final compilation, too many information needs to be analyzed within limited time
Field level activities are planned separately and when compiling, it sometimes results over planning than the approved budget
Various spelling of Name of townships/hospitals/SDPs required time for data cleaning
Different interpretation of activities leading to planning of activities out of scope
Quarter change – need to remove from previous quarter (to avoid misinterpretation and over/under planning in the following quarters)
Difficult to get real time/updated information on activity completion for reimbursed payment modalities

## Slide 9
THANK YOU VERY MUCH