## Slide 1: Finance & Work Plan Data Flow
November - 2016

## Slide 2: Main Components
Database

## Slide 3: Budget Code Samples
1.12.43  HIV
2.02.32  Malaria
3.09.021  TB
4.1.13.5.02  RAI
5.8  ACF-3MDG
5.9  MDRTB-3MDG

## Slide 4: Budget Code Samples
1.04.01
  1 - Disease
  04 – Cost Grouping (Health Products – Pharmaceutical Product)
  01 - Budget Line No.
4.1.11.5.01
  4 – RAI Mal
  1 – Module (Vendor Control)
  11 – Intervention (LLINs – Mass Campaign)
  5 – Cost Grouping (Health Products – Non-Pharmaceutical )
  01 – Activity Description

## Slide 5: Work-plan Preparation
Township level costed quarterly action/work-plan is prepared by TMO.
RO and TL negotiate with each TMOs and then consolidate these into State and Regional quarterly work-plan under the supervision and approval of S/RHD.
S/RHD negotiate among 4 programmes’ work-plan activities to harmonize with budget and to avoid the activities overlapping on S/R level.
Programme Manager negotiate with each RO and TL collectively in a 2 days workshop in NPT to finalize the costed consolidated quarterly National work-plan

## Slide 6: Work-plan Preparation (Cont.)
UNOPS reviews the National level work-plan to see if there are overlaps, provides feedback, discusses the challenges of MCF and negotiate with Programme Managers to approve the final quarterly work-plan.
4 Work-plans are merged by UNOPS.
The “merged” work-plan report is prepared using Microsoft Access.
The consolidated activity plans are in the form of “PDF” and “Excel”.
These consolidated activity plans are then shared to National Programme

## Slide 7: Role of stakeholders in MCF
QWP consolidate at Central
Direct disbursement
Reimbursement
One month before next quarter
Central, UNOPS &
WHO assistance
QWP review, approval and arrangement for MCF
QWP Implementation at different level
If needed,
QWP revision, can be done at state/regional level
QWP prepared by TMO
RO/TL consolidate the QWP
Central, UNOPS &
WHO assistance

## Slide 8: QWP Preparation – things to consider
Reference documents
  Approved Budget (Annex B)
  Approved Training Plan
  Narrative (Annex A)
  Approved Annual Work plan (Annex D)
Things to consider
  Ceiling budget
  Assumption (breakdown for each activity)
  Number of participants
  Ratio of Resource person and participant number
  Per diem rate
  As per quarterly budget/training plan
  Decision regarding mode of payment modalities

## Slide 9: Issues related to QWP
Responsible DoA holder/organizer to have QWP beforehand
Coordination with related MoH and other partners prior to preparation of QWP
Any changes necessary for quarterly work-plan implementation can be done at the State/Regional level within the DoH provided range of flexibility.
Feedback and amendment is possible (refer slide: QWP workflow and feedback)

## Slide 10: Work-plan in Excel prepared by National Programme
Data cleaning (Date, Townships, BGCode etc
Aligning the data column

## Slide 11: Work Plan FFA

## Slide 12: Activities in Region, Township & Budget
More useful for DOH
  State/Regional Health Director
  TMOs

## Slide 13: Activities in Region, Township & Budget

## Slide 14: List of Activity for FFAs

## Slide 15
Fund Requirement-by State & Region

## Slide 16
Fund Requirement-by FFA

## Slide 17: FFA Database

## Slide 18: FFA Database
* Send Data back to DM - monthly

## Slide 19: Activity Done Report

## Slide 20: Activity Done Report
Prepare reports by auto-generated access program
* 1LC ~ Late Claim
* 2WC ~ Wrong Claim (not submitted as per SOP)
* 3NAWC
* 4NAWC2
* 5GC ~ appropriately presented claim per quarter
* 6PM ~ Preventive Measures (per Program, per Quarter)
* Activity Summary Finance
* Activity Summary Program
* FFURML.xls
* DoneActivity.xls

## Slide 21: Reporting Timeline
Report/Data | Timeline
Work plan from Program Unit | 1st/2nd week of every quarter
Combined work plan/fund requirement | 2nd week of every quarter - to MCFU/FFA
Disbursement Data-FFURML from FFA | 20th of every month
Activity Done Report | 25th of every month
FFURML | 25th of every month

## Slide 22: Overall Data Flow
Budget
WP
Reports
Combine Data
FFA
DB
DB
DB
DB

## Slide 23
Thank you!